## Sheet1
Milestone | Date | Reason not accomplished
Project Start | 2021-01-26
Brainstorming | 2021-02-12
Proposal | 2021-02-05
Use diagram | 2021-03-25
SPMP | 2021-03-25
Meeting Professor | 2021-03-25
Update SPMP | 2021-03-26
Buy domain name | 2021-04-01
Acquire SSL | 2021-04-01
Connect to Wordpress | 2021-04-02
Design | 2021-04-10
Add gallery from IG | 2021-04-12
Map plug-in | 2021-04-13
Sign-up form | 2021-04-14
Locked appt plug-in | 2021-04-20 | Problem with password protected appointment making - password is required but sign-in is not
Payment plug-in | 2021-04-20 | Appointment not connected to payment - required plug-in costly
Try site as client | 2021-04-21
Show site to actual clients | 2021-04-22
Make changes | 2021-04-24 | Still some errors with smaller sections
Submittion | 2021-05-03 | Upcoming
Presentation | 2021-05-03 | Upcoming